

Chief Executive Officer

Richard Evans OBE

**CRAG Work Plan October 2021 – September 2022**

**TARGETS FOR October 2021-Septemeber 2022:**

**Action planner**

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | **Action** | **Objectives****(SMART goals)** | **Responsible members** | **Target date** | **Status / update** |
| 1 | To provide advice and information relating to the continuing education and professional development needs of advanced/consultant practitioners | * Publishing the revised guidance for the Support of New and Established consultant radiographer roles
* Organising quarterly CRAG virtual drop in Q&A session and annual study day with wider advanced/consultant practitioners’ network
* Update CRAG webpages
 | SC, LD and NR leading subgroup.LD, RM, RB and CFAll to contribute | April 2022July 2022September 2022 | Facilitate via online teams.Update webpages with new information (first update completed Feb 22 TOR). |
| 2 | To act as a source of expertise and leadership to SoR on future strategies of facilitating radiographers to extend their scope of practice as advanced/consultant practitioners  | * Engaging with all current SoR advisory groups/ responsible professional officers as appropriate
* CRAG recorded virtual webinars on career progression for students
* Representing the SoR vision and values on advanced/consultant practice in radiography when engaging with external stakeholders
 | Chair and Deputy ChairNB, LF, LS, RB.All | April 2022April 2022September 2022 | ToR raised at the officers meeting agenda October 2021ToR has spoken with the SoR officer for students – there is a series of webinars for students commencing spring/summer 2022 – CRAG session noted as possible for spring. |
| 3 | To collaborate with the SoR Research Advisory group on facilitating radiographer-led research | * Explore the provision of possible virtual research webinars showcasing research work by advanced/consultant practitioners
* Identifying joint projects between advisory groups to enhance research domains of advanced/consultant practitioners.
 | Chair and Deputy ChairChair and Deputy Chair | September 2022September 2022 |  |
| 4 | To provide professional advice and support to CoR in formulating professional and educational standards of advanced/consultant practitioners  | * CRAG acting as a pioneering expert group to validate the new consultant practitioner accreditation system
* Involving in designing bespoke assessor training package for advanced/consultant practitioner accreditation
* Collegiate work with diagnostic and therapeutic radiography service managers to raise awareness of’professional and educational standards required to fulfil the roles of advanced/consultant practitioners.
 | HY, LF, KN, VM, CF and SWBS, SC and NRChair and Deputy Chair | April 2022April 2022April 2022 | ToR contacted the officers for education and accreditation – they will be in touch when the new accreditation software is working and launched.Officers for education and accreditation are aware.ToR has spoken to AL, the officer who supports service managers – arranged a meeting to chat about collaboration. Positive with possible inclusion on managers study day agenda. |